## Project schedule
| Timeline Onlinestss.com Fase 1 - Ecommerce store | [13 empty] | Project start: | [7 empty] | 2025-02-17 | [9 empty] | Project end: | [7 empty] | 2025-06-30
| Project lead | Theo Darmawan | [12 empty] | Display week: | [7 empty] | 4 | [9 empty] | Working days left: | [7 empty] | 61
| Project description | Implement an e-commerce store
[15 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21
NO | TASK | DEPENDENCIES | DELIVERABLE | CATEGORY | ASSIGNED TO | PROGRESS | START (Actual) | END (Actual) | START | END |  | To Review | time axis 2025-03-10 to 2025-07-27
 | time axis 2025-03-10 to 2025-07-27
A1 | Define business goals and success metrics |  | Project summary | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-27 | FALSE | FALSE | 1 | 11
P2 | mengoptimalkan setingan plugin wordpress | akhir | Dokumentasi setting seperlunya | plugin | ES | 0% |  |  | 2025-06-23 | 2025-06-30 | FALSE | FALSE | 0 | 8
P1 | menetapkan daftar plugin wordpress | akhir | Rincian plugin dan gunanya | plugin | ES | 0% |  |  | 2025-06-18 | 2025-06-20 | FALSE | FALSE | 0 | 3
D3 | Memastikan semua persyaratan sistem terpenuhi | Semua | Completed requirements checklist | Testing | TD | 0% |  |  | 2025-06-10 | 2025-06-17 | FALSE | FALSE | 0 | 8
A5 | Create working timeline |  | Timeline | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1 | 5
A6 | Identify project tools and personnel |  | Project summary | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1 | 5
A7 | Identify key deliverables |  | Timeline | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1 | 5
A8 | Define project scope & requirements |  | Project summary | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1
A9 | Identify risks and dependencies |  | Project summary | Planning | TD | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1
U1 | Audit UI/UX yang sudah ada |  | Task list untuk perubahan | UI UX Design | ES,BP, TD | 100% |  |  | 2025-03-03 | 2025-03-17 | FALSE | TRUE | 1
B2 | set up project git repository |  | NA | Prework | TD | 100% | 2025-02-24 | 2025-02-25 | 2025-02-19 | 2025-02-21 | FALSE | FALSE | 1
D2 | Testing dummy transaction | D1 | NA | Testing | All | 0% |  |  | 2025-06-05 | 2025-06-10 | FALSE | FALSE | 0
D1 | Pelatihan personel terkait layanan penjualan | PB1-3 | Training material, documentation | Process | All | 0% | 2025-06-01 | 2025-06-25 | 2025-06-01 | 2025-06-25 | FALSE | FALSE | 0
P4 | Implementasi payment gateway Midtrans, real | P3 | Dokumentasi cara pemakaian dan maintenance, testing transaksi secara live | plugin | TD | 0% |  |  | 2025-05-19 | 2025-05-23 | FALSE | FALSE | 0
PB2 | Alur pengembalian barang bermasalah | B7 | NA | Front end, Back end | TD | 0% |  |  | 2025-05-15 | 2025-06-15 | FALSE | FALSE | 0
P6 | Implementasi pemesanan jasa pengiriman otomatis setelah pembayaran | B5 | Dokumentasi cara pemakaian dan maintenance, | plugin | TD | 0% |  |  | 2025-05-09 | 2025-05-13 | FALSE | FALSE | 0
PB3 | Alur registrasi pengguna baru | B8 | NA | Front end, Back end | TD | 0% |  |  | 2025-05-01 | 2025-05-15 | FALSE | FALSE | 0
W3 | Detail pembayaran & alamat dapat disimpan dalam profil pelanggan |  | NA | Front end, Back end | TD | 50% |  |  | 2025-04-30 | 2025-05-01 | FALSE | TRUE | 0
S1 | membenarkan isu security yg telah diidentifikasi di audit | B4 | Completed checklist | Front end, Back end | ES,TD | 0% |  |  | 2025-04-17 | 2025-06-17 | FALSE | FALSE | 0
W2 | Implementasi admin user dan admin panel untuk akun customer |  | NA | Front end, Back end | ES | 0% |  |  | 2025-04-15 | 2025-05-15 | FALSE | FALSE | 0 | 31
DB1 | set up staging server and push-to-live process | A3,A4 | Dokumentasi cara pemakaian dan maintenance, | Back end | ES | 100% |  |  | 2025-02-24 | 2025-02-26 | FALSE | FALSE | 1 | 3
U3 | Implementasi UI/UX baru | U2 | NA | Front end | Intern | 0% |  |  | 2025-04-14 | 2025-06-01 | FALSE | FALSE | 0 | 49
DB3 | Implementasi Backup berkala untuk database dan file di server | A3,A4 | Dokumentasi strategi backup, cara restore | Back end | ES | 0% |  |  | 2025-04-14 | 2025-04-18 | FALSE | FALSE | 0
W8 | Faktur penagihan otomatis untuk jumlah total pembelian dan biaya pengiriman. |  | Dokumentasi cara pemakaian dan maintenance, | Back end | ES | 0% |  |  | 2025-04-07 | 2025-04-11 | FALSE | FALSE | 0
W9 | Tersedia fitur input kode diskon saat checkout |  | Dokumentasi cara pemakaian dan maintenance, | Front end, Back end | ES | 0% |  |  | 2025-04-02 | 2025-04-04 | FALSE | FALSE | 0
P3 | Implementasi payment gateway Midtrans, sandbox |  | NA | plugin | ES | 100% | 2025-02-17 | 2025-02-21 | 2025-02-17 | 2025-02-21 | FALSE | FALSE | 1
U2 | Desain UI/UX baru | U1 | Rekomendasi perubahan dan desain baru | UI UX Design | Consultant UX | 0% |  |  | 2025-04-01 | 2025-05-01 | FALSE | FALSE | 0 | 31
P5 | Implementasi plugin epeken untuk estimasi biaya pengiriman |  | Dokumentasi cara pemakaian dan maintenance, | plugin | ES | 100% | 2025-02-17 | 2025-02-21 | 2025-04-02 | 2025-04-04 | FALSE | TRUE | 1
A4 | Pembuatan rencana pemeliharaan, upgrade, dan skalabilitas sistem IT |  | Rencana pemeliharaan dan kumpulan dokumentasi dari seluruh bagian sistem | Planning | TD | 30% | 2025-03-03 |  | 2025-04-01 | 2025-04-15 | FALSE | FALSE | 0
PB1 | Alur penjualan online | B6 | NA | Front end, Back end | TD | 0% |  |  | 2025-04-01 | 2025-05-01 | FALSE | FALSE | 0 | 31
S4 | memastikan standar keamanan checkout memenuhi PCI-DSS |  | Dokumentasi cara pemakaian dan maintenance, | Front end, Back end | TD | 0% |  |  | 2025-04-01 | 2025-04-07 | FALSE | FALSE | 0
W7 | Terdapat upload produk list berbasis CSV |  | Dokumentasi cara pemakaian dan maintenance, | Back end | ES | 0% |  |  | 2025-03-28 | 2025-04-01 | FALSE | FALSE | 0
W6 | Administrator toko dapat menambah, memperbarui, menghapus, dan mengurutkan daftar produk. |  | Dokumentasi cara pemakaian dan maintenance, | Front end, Back end | ES | 80% |  |  | 2025-03-24 | 2025-03-28 | FALSE | TRUE | 0
PF4 | create image / media optimization workflow |  | Dokumentasi cara pemakaian dan maintenance, | Back end | TD | 30% |  |  | 2025-03-19 | 2025-03-25 | FALSE | FALSE | 0
PF1 | membenarkan isu performa yg telah diidentifikasi di audit | B4 | Completed checklist | Front end, Back end | ES,TD | 0% |  |  | 2025-03-17 | 2025-04-17 | FALSE | FALSE | 0 | 32
PF3 | design & implementasi caching system |  | Dokumentasi cara pemakaian dan maintenance, | Back end | TD | 50% | 2025-03-10 |  | 2025-03-16 | 2025-03-20 | FALSE | FALSE | 0 | 5
PF2 | setup CDN |  | Dokumentasi cara pemakaian dan maintenance, | Back end | TD | 20% | 2025-03-10 |  | 2025-03-13 | 2025-03-20 | TRUE | FALSE | -1 | 8
S3 | Hak akses setiap tipe pengguna terdefinisi dengan jelas dan terbatas |  | Dokumentasi tipe user dan hak akses | Front end, Back end | BP | 0% |  |  | 2025-03-10 | 2025-03-15 | FALSE | FALSE | -1
B4 | security, performance audit |  | NA | Prework | TD | 40% | 2025-03-10 |  | 2025-03-06 | 2025-03-15 | FALSE | FALSE | -1 | 10
S2 | memastikan komunikasi server sudah menggunakan SSL | A3 | Dokumentasi cara pemakaian dan maintenance, | Front end, Back end | ES | 100% |  |  | 2025-02-24 | 2025-02-26 | FALSE | FALSE | 1 | 3
B3 | Mengkaitkan data user yang ada dalam sistem dengan customer id |  | Dokumentasi cara pemakaian dan maintenance, | Prework | ES,BP | 0% |  |  | 2025-03-04 | 2025-03-21 | TRUE | FALSE | -1 | 18
W5 | Sinkronisasi inventaris webstore berkala harian dengan database perusahaan utama. |  | Dokumentasi cara pemakaian dan maintenance, | Back end | ES,BP | 0% |  |  | 2025-03-04 | 2025-04-05 | TRUE | FALSE | -1 | 33
P8 | Integrasi Google Analytics untuk webstore |  | Dokumentasi cara pemakaian dan maintenance, | plugin | ES | 0% |  |  | 2025-03-03 | 2025-03-05 | FALSE | TRUE | -1 | 3
B5 | Menetapkan proses logistik pengiriman untuk pesanan online |  | flow chart | Prework | RC | 0% |  |  | 2025-02-28 | 2025-03-14 | FALSE | TRUE | -1
P7 | Install dan setup plugin untuk email promosi |  | Dokumentasi cara pemakaian dan maintenance, | plugin | ES | 0% |  |  | 2025-02-26 | 2025-02-28 | FALSE | TRUE | -1 | 3
W1 | Fitur wishlist untuk user |  | NA | Front end, Back end | ES | 100% | 2025-02-22 |  | 2025-02-22 | 2025-02-23 | FALSE | FALSE | 1
A3 | review hosting plan |  | Penjelasan hosting plan | Planning | TD, BP | 80% | 2025-02-26 |  | 2025-02-24 | 2025-03-03 | FALSE | FALSE | -1
B6 | Alur penjualan online |  | Flow chart | Process | BP | 100% | 2025-02-24 | 2025-03-17 | 2025-02-24 | 2025-02-26 | FALSE | TRUE | 1
W4 | Pencarian produk berdasarkan nama/kategori. |  | NA | Front end, Back end | Intern | 100% |  |  | 2025-03-24 | 2025-03-26 | FALSE | FALSE | 1
B7 | Alur pengembalian barang bermasalah |  | Flow chart | Process | BP | 100% | 2025-02-24 | 2025-03-17 | 2025-02-24 | 2025-02-26 | FALSE | TRUE | 1
B8 | Alur registrasi pengguna baru |  | Flow chart | Process | BP | 100% | 2025-02-24 | 2025-03-17 | 2025-02-24 | 2025-02-26 | FALSE | TRUE | 1
B1 | Mendesain arkitektur sistem IT untuk webstore untuk memenuhi semua syaran performa, kemudahan penggunaan dan keamanan |  | Desain sistem dengan penjelasan, presentasi ke stakeholder | Prework | TD | 60% | 2025-02-26 |  | 2025-02-21 | 2025-03-15 | FALSE | TRUE | -1
A2 | Develop budget |  | Project summary | Planning | TD | 0% |  |  | 2025-02-17 | 2025-02-28 | FALSE | FALSE | -1
DB2 | memisahkan transactions, users, and WP Databases | A3,A4 | NA | Back end | ES | 0% |  |  |  |  | #DIV/0! | FALSE | #DIV/0!
Planning and design
Prework
Pemetaan proses bisnis
Project Requirements
Sekuritas
Plugin Wordpress
Fitur webstore
Implementasi proses bisnis
Performa website
Database and Server
UI/UX
Deployment
Insert new rows ABOVE this one
Note on O6: Theo Darmawan: Red = Behind Schedule Yellow = On track Green = Finished
Note on C20: Theo Darmawan: hrs set meeting sama keuangan, daftar pertanyaan terkait alur penjualan
Note on C24: Theo Darmawan: harus bisa simpan multi alamat
Note on C27: Theo Darmawan: set up lagi kalo pindah hosting
Note on C34: Theo Darmawan: sudah jalan untuk user terbatas
Note on C35: Theo Darmawan: scaling hosting, server resources, databases, maintenance tasks, make a checklist. should be done progressively.
Note on C39: Theo Darmawan: sedang dicek apa daftar bisa diurutkan
Note on C44: Theo Darmawan: jangan lupa merubah field / halaman sesuai tipe user
Note on C45: Theo Darmawan: refer ke google pagespeed insights, search google security checklist
Note on C46: Theo Darmawan: pindah hosting hrs diulang
Note on C47: Theo Darmawan: data pelangaan yang ada harus dibenerin dulu. tabel user db dan form registrasi diupdate.
Note on C58: Theo Darmawan: still need to look into splitting the database and multiple app servers, and whether the basic managed hosting single server architecture works for projected traffic..
Note on K60: Theo Darmawan: on hold

## Constants
2025-03-29 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-18 | 2025-04-20 | 2025-05-01 | 2025-05-12 | 2025-05-13 | 2025-05-29 | 2025-05-30 | 2025-06-01 | 2025-06-06 | 2025-06-09 | 2025-06-27
Holiday dates in indo
Task Categories
System design
UI / UX design
Front end website
Bace end website
Business process design

## speed vlist
WordPress Site Speed Optimization Checklist
1. Hosting & Server
✅ Use a high-performance hosting provider (e.g., Cloudways, SiteGround, Kinsta). |  | move to hostinger after trialing astra theme?
✅ Enable server-side caching (if available, lscache). | y, lscache with redis
✅ Use the latest PHP version. |  | move to php 8.1 from 7.4?
✅ Optimize database performance (WP-Optimize or MySQL tuning). | y | look into using db indexes (later)
hosting plan is enough for daily use with headroom for high traffic and website upgrades |  | need to check server resource usage
fast web server (litespeed) | y
2. Caching & CDN
✅ Install a caching plugin (WP Rocket, W3 Total Cache, LiteSpeed Cache). | y, ls cache plugin | need to look and tune the cache settings, including esi
✅ Enable browser caching. | y, ls cache plugin browser tab
✅ Use a Content Delivery Network (CDN) like Cloudflare or BunnyCDN. | y, quic.cloud | need to tune cdn
3. Image & Media Optimization
✅ Compress images using ShortPixel, Imagify, or Smush. | y, quic.cloud
✅ Serve images in next-gen formats (WebP, AVIF). | y, lscache | look into image attributes that will be converted
✅ Use lazy loading for images and videos. | y, lscache
4. Plugins & Themes
✅ Remove unnecessary plugins (clean uninstall).
✅ Use a lightweight theme (Astra, GeneratePress, Kadence). | y, astra
✅ Keep themes and plugins updated.
5. Code Optimization
✅ Minify CSS, JavaScript, and HTML (Autoptimize or WP Rocket). | y
✅ Defer or async load JavaScript. | y | tune settings in ls cache
✅ Reduce external scripts (Google Fonts, third-party APIs). |  | check what js urls are used , modify ls cache settings
✅ Remove unused CSS with a performance plugin.
6. Database Optimization
✅ Delete post revisions, spam comments, and transients. | y | this process needs to be done periodically
✅ Schedule automatic database cleanups with WP-Optimize.
7. External & Third-Party Services
✅ Limit the use of external scripts (Facebook Pixel, chat widgets).
✅ Host Google Fonts locally if necessary.
8. Performance Testing & Monitoring
✅ Test speed with GTmetrix, PageSpeed Insights, or Pingdom. | y
✅ Monitor slow queries with Query Monitor.
✅ Check hosting performance with New Relic or similar tools.

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.
prework
prework is the work that lays the groundwork for the project. In that the tasks have linkages with future tasks and should be completed as early as possible, after planning.